## Sheet1
Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
laptop falls and damages internal hardware | Unable to login and proceed with work | Low | High | Developer | Try and work with another machine | Have a backup machine to carry on progress | Matrix keys
Missing issues in sprints while Jira started a sprint | The issues are not included in the outcome of your project | Medium | Low | Developer | Add it to the sprint that is currently running | Make sure your planning is done effectively and detailed before the sprint begins | High
Website gets hacked | Website gets corrupted and unable to submit project | High | High* | Developer | Quickly remove all links to the dependency and reset all personal information. | Make sure you work locally throughout the project as it doesn’t require any external source | Medium
Internet connection gets cut | All work that isnt local cannot be interacted with. | High | Low | Internet provider | Try find a friend, family or public place to work until the internet is resolved | Use hotspot from mobile Phone, call internet provider and find friends and family to work at. | Low
Trainer busy with others and cannot answer your emergency question | Can't move on to next parts of the project | Medium | High | Developer | Try internet and videos until trainer gets back to you | ensure the rest of your work is up to scratch to ensure you get the most marks possible
Conflicts in GitHub | Data being lost | Medium | Medium | Developer | Make sure to be consistent with commits and go back if needed. | contact trainer to resolve issue to not cause further damage.
Images get corrupted or lost | Losing documentation marks | Medium | Low | Developer | Try using MD language or Imgur | Use at least couple other Images or use alt in html
Missed Deadline | Incomplete work submitted | Medium | High | Developer | make sure all the tasks in MVP is checked out | Plan and work effectively. Move on if stuck with a problem and don’t spend too much time on smaller mark aspects of the project. Ask questions as the trainer will be available the whole week
Feeling unwell due to Ramadan | Not being able to complete the project | Low | High | Developer | Ensure the QA seniors are aware and have evidence/tests available for them | Try to work after fasting stops if possible.